## DT Azure Monitor Test Plan
Test Plan Milestone | Step | Description | Owner | Status | Comment
Prerequisites |  | Dependency pre-reqs for the integration
| 1 | Request service principal to be created with reader permissions, or a sufficient custom monitoring role tied to the target subscription to be monitored in Dynatrace. After creation, the client id, tenant id, and secret key details will need to be shared with the person configuring the integration in Dynatrace.
| 2 | Request/deploy/configure at least 1 Environment ActiveGate in the target environment, ensuring the ActiveGate has the Azure module enabled
| 3 | Submit the exeception request for the ActiveGate to bypass proxy to the Azure APIs
| 4 | Validate Environment ActiveGate connectivity to Azure APIs post proxy bypass completion
| 5 | User planned to configure the integration has Dynatrace "change monitoring settings" permissions
Configure Integration |  | Configure Azure Monitor integration in Dynatrace environment settings
| 1 | Access environment settings, followed by Cloud and virtualization, followed by the Azure selection
| 2 | Connect new Azure subscription instance via client id, tenand id, and secret key
| 3 | Validate successful connection
Validate Integration |  | Validate Azure entities, metrics, tags, and metadata
| 1 | Validate Azure entities
| 2 | Validate Azure metrics and charting
| 3 | Validate Azure tags and metadata
| 4 | Validate any supporting cloud service metrics
Post Implementation |  | Configure dashboards, custom alerts, operational support
| 1 | Support training and documentation needs
| 2 | Review the default recommended Azure custom alerting rules
| 3 | Configure custom alerts
| 4 | Configure alerting profiles
| 5 | Configure problem notifications
| 6 | Configure custom dashboard(s)
| 7 | Review problems being generated
| 8 | Review if there are any other custom configurations needed
| 9 | Review the DDU licensing being used from the integration